# Interim Report

# March 2002

Solar Keymark

Network co-operation about implementing the EN Standards and

Establishing the CEN/CENELEC Keymark for Solar Thermal Products

European Solar Industry Federation (ESIF)

Proposal no: AL/2000/144

Cluster 2: Solar Thermal Technology Promotion

Contract no: 4.1030/00-002/2000

PRIORITY AREA:

STU

(Development and dissemination of standards and certification)

Jan Erik Nielsen, Thursday, March 19th, 2002

# Project Proposal Summary

| Aim of the project The aim of the project is to open the European market for producers and dealers of solar thermal products by implementing the new EN standards and establishing a certification mark (KEYMARK) for solar thermal products. This “SOLAR KEYMARK” shall ensure compliance with the upcoming European standards for solar thermal products: EN12975, EN12976 and ENV 12977. To the consumers the Keymark act as a common EU quality certificate for solar thermal systems and components. The Keymark shall replace all the different national/regional “certifications” existing now. Expected results The direct results of the project will be: International co-operation about implementing the EN tests for solar thermal products. A large group of the main national European solar test institutes will be accredited to perform the tests according to the EN standards The SOLAR KEYMARK. This certification mark referring to conformity with the EN standards will be used as a quality label for solar thermal products A solar thermal product will need one test only according to the EN standards – this test will be valid for whole Europe And the most important indirect results Open market for solar thermal products Increased sale Lower price Improved quality Enhanced user confidence Dissemination potential The European Solar Industry Federation, representing approx. 300 European solar industries, together with 10 leading national solar test institutes propose this Solar Keymark project. They commit themselves to use their major influence to make the Solar Keymark valid through out all of Europe, replacing all the different national/regional “certifications” existing now. So do the associated partners: Active Solar Thermal Group, representing directly 18 European solar thermal industries and the test institute Testzentrum Saarbrücken. |
| --- |
| Financial details | Euro |
| Total project cost | 600,500 |
| Eligible cost (for European Commission support) | 600,500 |
| Support requested from the EC | 300,000 |
| Support requested from or granted by any other public body (please specify) | 0 |
| Expected income (participation fees, sales,etc ...) | 0 |
| Financial contribution of the proposer(s) | 300,500 |

# Contents

Project Proposal Summary	2

Contents	3

Introduction	4

Work Package 1: Network of test institutes	4

Work Package 2: CEN/CENELEC European Mark Scheme	5

Work Package 3: Dissemination of project results and marketing the “Solar Keymark” label	6

Attachments:	8

# Introduction

This is the interim report on the ALTENER project: “Solar Keymark - Network co-operation about implementing the EN Standards and establishing the CEN/CENELEC Keymark for Solar Thermal Products, Co-ordinator: European Solar Industry Federation (ESIF), Project manager: Danish Technological Institute, Proposal no: AL/2000/144, Part of the Cluster 2: Solar Thermal Technology Promotion, Contract no: 4,1030/00-002/2000”. The report describes the work done in the project so far corresponding to 70% of proposed work.

The project is running very well – some months ahead of the original time schedule.

# Work Package 1: Network of test institutes

The network of solar thermal test institutes is established and well functioning. The project has really become a platform for European test institutes to meet and exchange experience.

WP1.a Biggest priority has been given to collectors. The implementation of the collectors test methods of the European standards is already finished at all institutes and more than half of the institutes are already accredited.

WP1.b Second priority has been given factory made systems. The implementation of test methods is already finished at almost all labs (only two missing) and the first two labs are already accredited.

WP1.c Third priority has been given custom built systems. The test methods for these products are given in preliminary standards (ENV’s) and according to the general Keymark scheme rules it is not possible to Keymark products for which only ENV’s exists. So the focus for this group is to work with standards, improving them to the stage where they can obtain the EN status.

WP1.d The common database for computer models and measured test sequences is established, but not yet fully developed Appendix WP1.1: Databases – 1.draft.

The first draft list including the most important comments to the standards are produced  Appendix WP1.2: Comments to the standards – 1.draft.

Two meetings out of original planned three has been held so far.

WP1 milestones reached

- 1/4, 2001: Network established

- 8/6, 2001: Kick off meeting, 1. meeting report included in: Appendix G1: Interim Report October 2001

- 29-30/10 2001: 2. meeting, 2. meeting report: Appendix G2: Minutes of 2. meeting

- 31/3, 2002; All labs ready to test according to EN12975-2

- 31/3, 2002; 6 out of 11 labs accredited for testing according to EN12975-2

- 31/3, 2002; 6 out of 8 labs ready to test according to EN12976-2

- 31/3, 2002; 2 out of 7 labs accredited for testing according to EN12976-2

- 31/3, 2002; 2 out of 6 labs ready to test according to ENV12977-2

- 15/3, 2002: Databases for models and test sequences established 15/3, Appendix WP1.1: Databases – 1.draft.

WP1 Milestones missing

- All test methods implemented at all labs

- All labs accredited

- Final version of databases

- Last meeting with report

WP1 deliverables so far

- Meeting reports: Reports of first and second meeting: Appendix G1: Interim Report October 2001 and Appendix G2: Minutes of 2. meeting.

- A set of recommendations for revision of EN/ENV 1297x: First draft with the most important recommendations: Appendix WP1.2: Comments to the standards – 1.draft.

- Databases for models and test sequences: First version: Appendix WP1.1: Databases – 1.draft.

- Interim Report, October 2001: Appendix G1: Interim Report October 2001

- Project Interim Report, March 2002: This report

WP1 deliverables to come

- Last meeting report

- Final version of databases

- Final set of recommendations for revision of EN/ENV 1297x

# Work Package 2: CEN/CENELEC European Mark Scheme

The process of working out the CEN/CENELEC European Mark Scheme for Solar Thermal Products (The Specific CEN Keymark Scheme Rules for Solar Thermal Products) is working out very well. The CEN Certification Board (CCB) has accepted the development of a Solar Keymark certification scheme and the creation of a CEN Solar Keymark Work Group. And despite some confusion in the beginning of the project - due to essential changes in the general certification regulations at CEN level - the drafting process is now on track, and a - hopefully - final draft will be presented to the CEN Certification Board (CCB) in May 2002. An earlier draft has already passed the CCB and has been approved for further elaboration. The CCB may approve the draft presented in May, but to be on the safe side we calculate with a final approval in the autumn 2002.

Two meetings with the CEN Management Centre (CMC) have been held and the project proposal has been presented and approved at a CCB meeting.

It has been discussed how to assure the sustainability of the Solar Keymark certification after the end of this project – this is reported in the WP3 part below.

WP2 milestones reached

- 11/9, 2001: Project proposal for a CEN/CENELEC European Mark Scheme for Solar Thermal Products delivered and presented at the CCB meeting in Brussels.

- 11/9, 2001: Project proposal for a CEN/CENELEC European Mark Scheme for Solar Thermal Products approved by CCB

Phase one completed

- 12/9, 2001: Official CEN Solar Keymark Work Group established (Jan Erik Nielsen, DTI, project manager of the Altener Solar Keymark project; Andreas Constantinides, representing the European Solar Industry Federation (ESIF); Teun Bokhoven, representing the industry association the Active Solar Thermal Group (ASTIG)

- 5/3, 2002: First draft of the Specific CEN Keymark Scheme Rules for Solar Thermal Products approved by CCB for further elaboration

WP2 Milestones missing

- Final preparation (1/5, 2002 and maybe again before autumn 2002)

- Final approval (16/5 or autumn 2002)

WP2 deliverables so far

- Meeting reports: Reports of first and second meeting: Appendix G1: Interim Report October 2001 and Appendix G2: Minutes of 2. meeting.

- Project proposal for a CEN/CENELEC European Mark Scheme: Appendix WP2.1: Proposal for a CEN/CENELEC European Mark Scheme for Solar Thermal Products

- Approved project proposal for a CEN/CENELEC European Mark Scheme

- Draft Mark Scheme rules prepared (and approved by CCB ): Appendix WP2.2: Specific CEN Keymark Scheme Rules for Solar Thermal Products.

WP2 deliverables to come

- Approved CEN/CENELEC European Mark Scheme for Solar Thermal Products

# Work Package 3: Dissemination of project results and marketing the “Solar Keymark” label

Designing the label: The minimum requirements for the contents of information are actually already given in the standards EN12975-1 and EN12976-1 for collectors and systems respectively. Discussion is going on right now if a kind of classification/characterisation should be added. First draft of a collector Keymark label is given in Appendix WP3.1: Label draft.

Focus in the Solar Keymark promotion campaign has so far been directed to the manufacturers and authoryties. The national industry associations are informing their members about the new European standards and recommending the use of the Keymark. See list of arrangements already held in Appendix WP3.2: List of National Actions.

The national authorities and standards committees are “attacked” by the participating national test institutes, all of them having actually very big influence on the respective national authorities. The goal is to make the national certification schemes equal to the Keymark scheme. Some success has been achieved already, but there is still work to be done. See list of deviating national requirements in Appendix WP3.3: National Deviations.

Co-operation with the Altener Soltherm initiative has started and agreement obtained that promotion of the Solar Keymark will be included in the campaigns done here. This means that the Solar Keymark will reach the public, as the campaigns done within the Soltherm initiative will recommend the users and installers to choose Keymarked solar products. See http://www.mysolar.com/soltherm/tools_guidelines.asp.

Also the Solar Keymark has been promoted more generally at international conferences, see list of papers given in Appendix WP3.4: List of International Papers.

Although it was not foreseen in the project proposal a web site has been published: www.solarkeymark.org, because this is very effective in the dissemination process.

It is very important to establish a sustainable structure/organisation for the administration of the Solar Keymark to secure its survival in after this project has finished. The project manager has discussed this issue with the industrial associations and they have agreed on a proposal for establishing a secretariat very close linked to the industrial organisations and financed by licence fees from manufacturers. In Appendix WP3.5: Proposal for future administration of the Solar Keymark this proposal is outlined in more detail.

WP3 milestones reached

- Updated project information twice a year: Appendix G1: Interim Report October 2001 and this report. Web site published: www.solarkeymark.org

- 4 international papers given: Appendix WP3.4: List of International Papers.

- Draft campaign material ready for download: www.solarkeymark.org

WP3 Milestones missing

- Replacement of national certificates with the Solar Keymark: Due to changes (out of our hands) at CEN level, a Keymark has to be used in conjunction with a national certificate (fulfilling the Keymark requirements). However the participants are all using their influence to make the national certification schemes as close to the Keymark as possible. In Appendix WP3.3: National Deviations an investigation of the national deviations are presented.

- Final campaign material ready

WP3 deliverables so far

- Meeting reports: Reports of first and second meeting: Appendix G1: Interim Report October 2001 and Appendix G2: Minutes of 2. meeting.

- Web site: www.solarkeymark.org

- Solar Keymark design: First draft given in Appendix WP3.1: Label draft.

- Newsletters and meeting reports from ESIF to members. Newsletters and meeting reports from ASTIG to members (obtainable from ESF and ASTIG9.

- 4 international presentations/papers papers given: Appendix WP3.4: List of International Papers

- Draft campaign material for download from: www.solarkeymark.org

- International actions: Co-operation with the Altener Soltherm project and the Altener Sun in Action II project

- National actions: See list in Appendix WP3.2: List of National Actions

- Appendix WP3.5: Proposal for future administration of the Solar Keymark

WP3 deliverables to come

- Final Solar Keymark Label Design

- A few more international papers

- Final Campaign material

# Attachments:

- Appendix G1: Interim Report October 2001 (incl. minutes of 1. meeting)

- Appendix G2: Minutes of 2. meeting

- Appendix WP1.1: Databases – 1.draft

- Appendix WP1.2: Comments to the standards – 1.draft

- Appendix WP2.1: Proposal for a CEN/CENELEC European Mark Scheme for Solar Thermal Products

- Appendix WP2.2: Specific CEN Keymark Scheme Rules for Solar Thermal Products

- Appendix WP3.1: Label draft

- Appendix WP3.2: List of National Actions

- Appendix WP3.3: National Deviations

- Appendix WP3.4: List of International Papers

- Appendix WP3.5: Proposal for future administration of the Solar Keymark