## 23 SKN
[5 empty] | 2017-05-12 | SKN_N0286.R8
SKN ACTION LIST |  |  |  | Last SKN meeting: |  | 2017-03-08&09 FREIBURG (22 SKN Meeting)
|  |  |  | Next SKN meeting: |  | 2017-10-17&18 CYPRUS (23 SKN Meeting)
Item |  | Resolution or Decision taken | Level of Importance | Long, Medium or Short term Project | WG Leader or Responsible of action | Follow-up
5 | Result on voting by correspondence on issues from meeting 21A(web) | M21A.R2: To add a new paragraph in Section 13.7 of specific scheme rules to deal with discontinuous performance curve behaviour within ScenoCalc: | High | Short Term | Jan Erik Nielsen | OK (JE)
7 | Structure/organization of SKN meetings | D1- Change of structure for SKN Meetings | High | Short Term | *Pedro Dias |  | *Note from Jaime: The new WEB system has to be tried at the next SKN meeting. This will require some fine tuning from ESTIF.
8 | Date and place of next meetings | • 23rd SKN meeting: October 17th, 13:00 hrs to October 18th, 14:00 hrs, 2017, Larnaca, TUV Cyprus • 24nd SKN meeting: March 6th 13:00 to March 7th 14:00, 2018 - Madrid, AENOR, • 25th SKN meeting: October 2018. Web meeting | High | Short Term | Jan Erik Nielsen and Pedro Dias | Agenda for 23rd meeting being prepared (JE)
9 | Include Liaison officers in list in 2.2 of SKN internal rules | M22.R1 - Include Liaison officers in list in clause 2.2 of SKN internal rules | High | Short Term | Jan Erik Nielsen | OK (JE)
10 | Resolution regarding voting rules and web meetings of internal working rules | M22.D2 – To create a Participation Rules WG to elaborate a Resolution in order to adapt to the new structure of SKN Web meetings and to modify the voting preconditions | High | Short Term | Katharina Meyer
11 | Proposal for elaborating lists of resolutions | M22.D3- New Sections with lists of Resolutions and procedure for updates by SKN Manager | High | Short Term | Jan Erik Nielsen | OK (JE) Note from Jaime- Please remember that any changes in Scheme Rules have to be communicated to SKN members. See M22.D3. I think that this was not done. (I think it is best to clearly specify which documents are new in this communication)
12 | Proposal for decision / SCF steering group for SCF project applications (8th call) | M22.D4- Funding of proposals from the 8th SCF call | High | Medium | Pedro Dias | Have all Projects been signed?
12 | Proposal for decision / SCF steering group for SCF project applications (8th call) | M22-D6- Creation of a SHAMCI WG | Medium | Short Term | Ashraf Kraidy
13 | Report and Decision/Resolutions proposals by SCF Rules WG to improve the SCF Working rules | M22.R2- New revision of SCF_N0001R15_WorkingRules | High | Short Term | Jan Erik Nielsen | OK (JE) - Now SCF_N0001R16_WorkingRules
13 | Report and Decision/Resolutions proposals by SCF Rules WG to improve the SCF Working rules | Voting of SCF Chairman. Not in the minutes but it was discussed at SCF Steering Group meeting and procedure included in SCF Rules. | High | Short Term | Jan Erik Nielsen | **this was added in R.9**
15 | Report and Decision/Resolution from new 10% Rule WG to revise the 10% Rule of section 6.3 of Solar Keymark Scheme Rules and to study financial possibilities for dealing with complaints / Harald Drück | *M21.D1 – Establishment of new WG to revise the 10% Rule of section 6.3 of Solar Keymark Scheme Rules and to study financial possibilities for dealing with complaints | High | Short Term | Harald Drueck | SCF project approved | *Note from Jaime: Continue work from M21 since no outcome presented in M22
16 | Report and Decision/Resolution proposals from Air Collectors WG | * M21.D5 – Create a WG for air collectors (Continue work of WG) | Medium | Short Term | Korbinian Krammer |  | *Note from Jaime: Continue work from M21 since no outcome presented in M22
17 | Report and Decision/Resolution proposals from PVT WG | *M21A.D1 Reactivate WG for PVT to improve Annex J | High | Short Term | Ulrich Fritzsche |  | *Note from Jaime: Continue work from M21A and M22
18 | Report and Decision/Resolution proposal for exchange of insulation material in collectors “Equivalent insulation” | M22.R3 – Approval of new Annex K of Solar Keymark Scheme Rules for exchange of insulation materials in certified collectors | High | Short Term | Jan Erik Nielsen | Pending !!! (JE) Will solve asap
19 | Report and Decision/Resolution proposal for coloured glass famlilies on Glass WG | M22.R4 – Approval of new Annex L of Solar Keymark Scheme Rules for families of coloured glass | High | Short Term | Jan Erik Nielsen/ Katharina Meyaer | OK (JE)
20 | Report and Resolution on data sheets | M22.D8 – Procedure for funding changes in ScenoCalc | High | Short Term | Pedro Dias/Jan Erik Nielsen | A new discussion area has to be created in web site and it has to be communicated to the SKN
23 | Report and Decision/Resolution proposal from CB WG on Proposal by AB to do every second inspection visit via web. | No Decision taken but Project under way by Ulrich Fritzsche and Andreas Bohren with DinCertco for pilot project | Medium | Short Term | Ulrich Fritzsche/Andreas Bohren/Katharina Meyer
24 | Transition from EN 12975 to EN ISO 9806 in cases of OBL/OEM Certificates when subsidy grants or tenders make reference to EN 12975 or aperture area / JF | M22.R5 – Modification of Annex H of SK Scheme Rules to comply with M20.D2 for all new certificates to have latest version of data sheets as annex | Average | Short Term | Jan Erik Nielsen | OK (JE)
24 | Transition from EN 12975 to EN ISO 9806 in cases of OBL/OEM Certificates when subsidy grants or tenders make reference to EN 12975 or aperture area / JF | M22.R6 – Modification of Annex G of SK Scheme Rules to comply with M20.D2 for all new certificates to have latest version of data sheets as annex | Average | Short Term | Jan Erik Nielsen | OK (JE)
25 | Proposal for decisions from the Experience Circle of the German speaking Test Laboratories for Solar Thermal Systems and Components” (EK-TSuB – Prüflaboratorien) | M22.R8 - Extension of clause 4.3.1 (System families (EN 12976 - Factory made systems) of the Solar Keymark Scheme Rules | High | Short Term | Jan Erik Nielsen | OK (JE)
25 | Proposal for decisions from the Experience Circle of the German speaking Test Laboratories for Solar Thermal Systems and Components” (EK-TSuB – Prüflaboratorien) | M22.D10- System data sheet WG to prepare the work related to Resolution M22.R7 | High | Short Term | Maria Joao Carvalho | 6/4 Request for revising data sheet to Maria from JE 6/4 Maria promise revised data sheet template within a month. 12/5 JE send reminder to Maria (JE)
29 | Update on Complaints | Creation of Complaint Committee and its follow up work | High | Short Term | Soeren Scholz | Complaint Committee work ongoing
31 | 'Inter-Laboratory Comparison - ILC on Data Analysis'' | SCF- Project to be presented at next SKN Meeting | Medium | Medium | Andreas Bohren